SIGNAL GARDEN  /  PROJECT BRIEF  /  01

Make the night feel alive.

A community light and sound evening · 14 November 2026

## The idea

Signal Garden turns an ordinary neighborhood courtyard into a one-night trail of light, sound, and small creative experiments. Guests follow four stations, meet local makers, and leave with a simple project to try at home.

## What success looks like

Welcome 320 guests across two timed entry windows.

Keep the installation accessible, low-glare, and easy to navigate.

Stay under the $8,600 budget ceiling and fund next year's workshop.

## The evening, at a glance

| TIME | MOMENT | OWNER |
| --- | --- | --- |
| 17:30 | Doors and orientation | Front of house |
| 18:00 | Light trail opens | Installation crew |
| 19:15 | Maker talks and live demo | Program team |
| 20:30 | Final walkthrough | All teams |

## Decision for Friday

Confirm the accessible route and approve the weather cover before supplier deposits. The budget model and presentation use this same plan.